## Timeline
Week | Area | Task | Status | Notes | Dyno Simulator Progress
0 | Requirements | Review Version 1.0 requirements and confirm core / stretch / out-of-scope boundaries | Complete | Relies on tbcs | Total tasks | 65
0 | TBCs | Create questions list for Force range/sign, detailed Speed Mode capture behaviour, E-stop reset workflow and WOT profile | Complete | Confirmed: Force rate = N/s; Speed Mode minimum = 1 km/h with ~10+ km/h preferred practice; Light Drive tolerance = +/-15%; Light Drive/WOT countdown = 5 s; indicators = Healthy / No Alarms / AUX / Dyno; target PC = Windows 10, 16 GB RAM. | Complete | 13
0 | Architecture | Identify major components: Simulation Core, UI, Virtual Driver and 3D Visualisation | Complete |  | In Progress | 0
0 | Architecture | Write one clear responsibility for each major component | Complete |  | Remaining | 52
0 | Data ownership | Decide who owns CurrentSpeed, CurrentAcceleration, CurrentForce, Gradient, RigState and CurrentMode | Complete
0 | Architecture | Map commands/data flow between UI, simulation, virtual driver and 3D visuals | Complete |  | Overall completion | 20%
0 | UI | Create rough main-screen wireframe | Complete | Just needs dyno and vehicle drawing
0 | User flows | Map Start -> RLS, Speed, Force, Light Drive, WOT, Abort, Stop and E-stop flows | Complete
0 | Testing | Choose a simple acceptance-test format | Complete |  | Confirmed Design Inputs
0 | Setup | Confirm Unreal version, project name, Git approach and folder structure | Complete |  | Force rate | N/s
0 | Deployment | Begin investigating internal approval for packaged Unreal/Windows app | Complete | Seems no approval would be needed | Speed Mode minimum | 1 km/h
0 | Portfolio | Decide what non-proprietary development evidence to retain | Complete |  | Preferred Speed capture | ~10+ km/h
0 | Backlog | Break Week 1 into small actionable tasks | Complete |  | Light Drive tolerance | +/-15%
1 | Foundation | Create Unreal Engine 5 project and Git repository | Not Started |  | Light Drive countdown | 5 s
1 | Foundation | Create folder structure for UI, Blueprints, 3D assets, config and notes | Not Started |  | WOT countdown | 5 s
1 | UI | Build main UMG layout | Not Started |  | Target OS | Windows 10
1 | Simulation | Define Rig State, Mode, Command and core simulation variables | Not Started |  | Target RAM | 16 GB
1 | Simulation | Implement OFF -> Start -> AUX -> Dyno -> RLS, with Healthy / No Alarms status conditions | Not Started | Normal startup: AUX before Dyno. Normal shutdown: Dyno off before AUX. Healthy and No Alarms are normally on unless a relevant condition/fault exists. | Status indicators | Healthy / No Alarms / AUX / Dyno
1 | UI | Add four-square status indicators: Healthy, No Alarms, AUX and Dyno | Not Started | Healthy = overall dyno startable condition. No Alarms = alarm/fault status; some alarms may not stop rig operation. | Startup order | AUX then Dyno
2 | Speed Mode | Implement lower speed, upper speed and rate inputs | Not Started |  | Shutdown order | Dyno then AUX
2 | Speed Mode | Implement latched Raise / Hold / Lower states | Not Started
2 | Speed Mode | Implement 1 km/h minimum-speed interlock | Not Started | Preferred operator practice is to capture Speed Mode around 10+ km/h where practical.
2 | Speed Mode | Capture approximate current speed on mode entry | Not Started
2 | Speed Mode | Add LOAD OFF notification at upper limit | Not Started
2 | Visuals | Connect speed to provisional rollers/wheels and instrumentation | Not Started
3 | RLS | Implement Gradient limits and %/s rate | Not Started
3 | RLS | Implement Gradient Raise / Hold / Lower | Not Started
3 | Simulation | Create predictable coast-down behaviour | Not Started
3 | Simulation | Establish live Speed, Acceleration, Force, Gradient, Power and Restraint values | Not Started
3 | Simulation | Keep simulation relationships configurable | Not Started
4 | Light Drive | Build acceleration and upper-speed setup | Not Started
4 | Light Drive | Implement Go -> 5-second countdown -> accelerate -> load-off -> coast | Not Started
4 | Light Drive | Add configurable human-like acceleration variation (initially +/-15%) | Not Started
4 | Light Drive | Implement Abort | Not Started
4 | WOT | Implement WOT using shared virtual-driver logic | Not Started
4 | WOT | Make WOT acceleration profile configurable; confirm representative profile Monday | Not Started
4 | Testing | Test Abort during countdown and acceleration | Not Started
5 | Force Mode | Confirm Force sign convention and force ranges; Force rate is confirmed as N/s | Not Started
5 | Force Mode | Implement Force limits, rate and Raise / Hold / Lower | Not Started
5 | Force Mode | Allow front/rear force to differ and calculate combined force | Not Started
5 | Visuals | Make Force affect vehicle loading/resistance visuals | Not Started
5 | Shutdown | Implement Stop -> Neutral warning -> coast-down -> OFF | Not Started
5 | E-stop | Implement rapid deceleration -> Emergency Stopped | Not Started
6 | 3D | Replace placeholders with generic vehicle, rollers and restraint/post | Not Started
6 | Camera | Implement lightweight fixed three-quarter camera | Not Started
6 | 3D | Connect wheel/roller rotation to simulated speed | Not Started
6 | 3D | Connect vehicle pitch/rise/loading to acceleration/load | Not Started
6 | 3D | Show coast-down visually | Not Started
6 | Instrumentation | Build analogue-style dials plus numeric values | Not Started
6 | Performance | Keep visual fidelity suitable for basic PCs | Not Started
7 | Testing | Run complete operator workflows | Not Started
7 | Testing | Test invalid inputs and edge cases | Not Started
7 | UI | Improve active states, labels, units, notifications and validation | Not Started
7 | Status | Refine Healthy / No Alarms / AUX / Dyno status behaviour and edge cases | Not Started
7 | User testing | Have a knowledgeable operator/mentor use it independently | Not Started
7 | User testing | Record and fix highest-impact issues | Not Started
8 | Release | Freeze Version 1.0 features | Not Started
8 | Testing | Turn requirements into final verification checklist | Not Started
8 | Testing | Fix remaining functional bugs | Not Started
8 | Performance | Optimise for target Windows 10 / 16 GB RAM departmental PC | Not Started
8 | Deployment | Package and test standalone Windows build outside Unreal Editor | Not Started
8 | Deployment | Continue/confirm internal IT approval route | Not Started
8 | Documentation | Document known limitations and remaining TBCs | Not Started
8 | Portfolio | Prepare sanitised portfolio case study if appropriate | Not Started
8 | Stretch | Only if core is stable: consider RPM/gear OR second camera | Not Started

## Weekly Summary
Week | Focus | Tasks | Completed
0 | Planning + Architecture | 13 | 13
1 | Foundation + UI | 6 | 0
2 | Speed Mode | 6 | 0
3 | RLS + Gradient | 5 | 0
4 | Light Drive + WOT | 7 | 0
5 | Force + Shutdown | 6 | 0
6 | 3D + Instrumentation | 7 | 0
7 | Workflow + Polish | 6 | 0
8 | Test + Package | 9 | 0